# 48-hour team charter and work plan

A small operating agreement for a team of three to five

Package scope: This package is the operating guide for Q3 nontechnical hackathon teams. A technical buildathon team, including Digital SRE, follows its dedicated charter and event instructions. Shared safety and collaboration practices help only where they do not conflict with that charter.

Use this guide and the matching template to make scope, ownership, working rhythm, and evidence visible before the build gets busy. A small clear first version is stronger than a broad idea with no proof.

# Before kickoff: establish the operating foundation

Complete preflight: sign in, open the shared workspace, confirm expected tool and source access, and identify a fallback for an access or capacity issue.

Fill out TEAM_CHARTER.md in 00_Admin/ with the team/channel ID, use case, member names, roles, time zones, working hours, backups, and final submission owner.

Read the assigned brief and sponsor inputs. Capture only preparation decisions before the official kickoff; do not start building the submission or working with sponsor data early.

Use the current team Teams channel for the official kickoff time, meeting link, shared FAQ, and event updates. This guide does not establish a separate start time.

# Set the charter in the first working session

| Charter item | Question to answer |
| --- | --- |
| User | Who has the problem or makes the decision this result should help? |
| Problem | What is slow, difficult, repetitive, risky, or unclear today? |
| First useful result | What can the team reasonably demonstrate or hand off before the deadline? |
| Success evidence | What would show the result is clearer, faster, safer, more useful, or more reusable? |
| Boundaries | Which data, tools, connectors, systems, or actions are out of scope? |
| Brief-specific requirement | What must this use case demonstrate or include, beyond the general package rules? |
| Decision owner | Who keeps the team moving when a scope choice is needed? |

# Use roles, not hierarchy

| Role | Owns |
| --- | --- |
| Project coordinator | STATUS.md, working rhythm, handoffs, blocker visibility, and continuity. |
| Workflow or domain lead | User need, sponsor questions, process logic, and source interpretation. |
| Builder or integrator | Chosen artifact, technical setup, file structure, shared-file integration, and backup. |
| Tester and reviewer | Realistic cases, test log, sources, permissions, limitations, and reviewer-access check. |
| Story and demo lead | Final README, demonstration path, assigned-brief check, and reviewer starting point. |

In a three-person team, combine roles. In a five-person team, do not create a separate workstream without a named output, owner, backup, and handoff.

# Plan the 48 hours around proof

| When | Team focus | Leave behind |
| --- | --- | --- |
| Before official kickoff | Access, workspace, roles, time zones, folder structure, and sponsor questions. | Team charter and preflight notes. |
| First 2 build hours | Agree on user, smallest result, scope, data boundary, first task, and first handoff. | STATUS.md, decision log, and sponsor questions. |
| Day 1 | Build or design the first usable version. Try an approved example. | Working artifact, initial test log, handoff. |
| Start of Day 2 | Review evidence. Reduce scope if needed. Decide what a reviewer must see. | Updated status, decision log, final build list. |
| Final build period | Finish artifact, test main and edge paths, write README, prepare review path. | Final package in 03_Final_Submission/. |
| Before 11:59 PM PT | Verify reviewer access, post final message, freeze files, and complete handoff. | Valid final package in the Teams channel. |

# Definition of done

The team can explain the problem, intended user, and chosen first version in plain language.

The result satisfies the assigned brief and confirmed sponsor clarifications, not only the general package guidance.

A reviewer who did not create the asset can find the final folder, understand the setup or sign-in needs, and review an accessible artifact or fallback walkthrough from Teams.

The team has shown a real example, test, walkthrough, or other evidence and has separated demonstrated behavior from assumptions and future ideas.

The final README documents sources, permissions, reused versus created assets, limits, ownership, and the next step.

Scope reset is a strength: If the current plan cannot be built, tested, explained, and handed off by the deadline, reduce it. Keep the most valuable user decision or workflow step and demonstrate that well.

# Continuity

If a teammate is absent, record the impact in STATUS.md, notify the team, reassign only safe work, and request organizer direction before changing the official team roster.

If a sponsor cannot answer in time, record the question, identify who can decide it, and choose a safe parallel task. Do not invent permission or expand scope.

Only organizers can authorize a material team change or exception. Use the team channel's current event support route; contact Austin.braham@realpage.com for a workspace, submission, or event-routing problem.

Submission rule: The final package must be in the team Teams channel by 11:59 PM PT on Thursday, September 17, 2026. A package outside that channel is not a valid submission. Review begins Friday, September 18, 2026.